Pre-Workshop Planning

  - Initial discussions on workshop/event scope

  - Communicate requirements to local host to host a workshop

  - Work with contacts provided by local host to ensure that requirements are met and verified in a timely manner

  - Work with NSRC core staff to finalize instructor team

  - Prepare a workshop wiki

  - Assign topics to instructors and create workshop agenda in conjunction with instructor team

  - Assist instructor team with access to NSRC Git repositories as necessary

  - Make sure instructor staff book travel

  - Remote lab access

  - Connectivity

  - Power

  - Lodging and meals

  - Transport

  - Equipment shipping

  - Books

  - Kit Preparation

  - List of participants

  - Mailing list

  - Network diagrams or other participant submitted documents

  - Social events planning

  - Instructor briefing

  - Materials to print on-site

  - Work with local host to prepare for certificates

During the Workshop

  - Workshop preparation day

  - Lead or coordinate opening session

  - Consider an initial, short questionnaire set of questions to determine participant level

  - Verify participant list details

  - Work with local host to create, print and have signed certificates during the week

  - Workshop wiki and web site

  - Videos and photos

  - Group photo

  - Social media

  - Materials

  - Arrange for distribution of workshop books

  - Closing exam

  - Survey/evaluation

  - Event notes

Post Workshop

  - Ensure that local workshop wiki is synchronized back to nsrc.org public copy

  - Ensure that workshop group photo is published

  - Post to Facebook and Google+ a workshop update, or work with NSRC core staff to do this

  - Upload photos to photos.nsrc.org

  - Supply post event notes / report

  - Follow up on workshop mailing list with appropriate post-workshop items as needed

  - Archive the survey, and deactivate it, after a week or so

| ITEM | SUGGESTED DATES |
| --- | --- |
| Pre-Workshop Planning* | Months/Weeks Prior |
| Initial discussions on workshop/event scope | 3 months |
| Communicate requirements to local host to host a workshop | 2 1/2 moths |
| Work with contacts provided by local host to ensure that requirements are met and verified in a timely manner | Start at 2 months |
| Work with NSRC core staff to finalize instructor team | 2 months |
| Prepare a workshop wiki | 12-4 weeks |
| Assign topics to instructors and create workshop agenda in conjunction with instructor team | 4-2 weeks |
| Assist instructor team with access to NSRC Git repositories as necessary | 4-2 |
| Make sure instructor staff book travel | 12-4 weeks |
| Remote lab access | 4 weeks |
| Connectivity | 8-4 weeks |
| Power | 8-4 weeks |
| Lodging and meals | 12-4 weeks |
| Transport | 8-4 weeks |
| Equipment shipping | 4 weeks |
| Books | 4-2 weeks |
| Kit preparation | 2 weeks |
| List of participants | 2-1 weeks |
| Mailing list | 2-1 weeks |
| Network diagrams or other participant submitted documents | 2-1 weeks |
| Social events planning | 4-2 weeks |
| Instructor briefing | 2 weeks |
| Materials to print on-site | 1 week |
| Work with local host to prepare for certificates | 2-1 weeks |
| During the Workshop | Timeline |
| Workshop preparation day | 1 day before workshop |
| Lead or coordinate opening session | Day 1 |
| Consider an initial, short questionnaire set of questions to determine participant level | Day 1 |
| Verify participant list details | Day 2 |
| Work with local host to create, print and have signed certificates during the week | Day 3-4 |
| Workshop wiki and web site | All week |
| Videos and photos | All week |
| Group photo | Before last day |
| Social media | All week |
| Materials | All week |
| Arrange for distribution of workshop books | Last day |
| Closing exam | Last day |
| Survey/evaluation | Last day |
| Event notes | All week |
| Post Workshop | Timeline |
| Ensure that local workshop wiki is synchronized back to nsrc.org public copy | Last day |
| Ensure that workshop group photo is published | Day 4 or 5 |
| Post to Facebook and Google+ a workshop update, or work with NSRC core staff to do this | Last day |
| Upload photos to photos.nsrc.org | within 1 week |
| Supply post event notes / report | within 1 week |
| Follow up on workshop mailing list with appropriate post-workshop items as needed | within 3 to 4 days |
| Archive the survey, and deactivate it, after a week or so | within 1-2 weeks |